## Product Backlog
PBI ID | Epic | User Story | Priority (MoSCoW) | Story Points | Sprint | Status | Assigned To | Acceptance Criteria
PBI-001 | Technical Foundation | As a developer, I want an Expo + TypeScript mobile workspace with shared navigation and theme scaffolding, so that the team can build V1 features on a consistent app shell. | Must | 5 | 1 | Done |  | 1. Expo mobile app is initialized with TypeScript and runs on iOS and Android simulators. 2. App shell includes auth stack, onboarding stack, and main tab navigation placeholders. 3. Shared theme tokens exist for color, spacing, typography, and card layout. 4. Project structure separates screens, feature modules, providers, and shared UI components. 5. README or setup notes document the local run command and environment expectations.
PBI-002 | Technical Foundation | As a developer, I want Supabase client configuration and session persistence wired into the mobile app, so that authenticated flows are stable across app restarts. | Must | 5 | 1 | Done |  | 1. Supabase client is configured for React Native session persistence. 2. Environment variables are loaded safely for local development and build environments. 3. Session refresh works when the app returns to the foreground. 4. Unauthenticated state and authenticated state are exposed through a provider or store. 5. App startup restores an existing valid session without requiring the user to log in again.
PBI-003 | Technical Foundation | As a developer, I want shared domain keys, score types, and action taxonomy defined in one place, so that client and backend logic stay consistent. | Must | 3 | 1 | Done |  | 1. Five domain keys are defined once and reused throughout the app and backend. 2. Shared types cover onboarding ratings, daily check-ins, action logs, and weekly summaries. 3. Score-related enums and action event names are centralized. 4. Unsupported or misspelled domain keys are rejected by type checks or validation. 5. Shared constants are importable from both mobile and backend code paths.
PBI-004 | Technical Foundation | As a developer, I want V1 database schema, row-level security, and profile bootstrap logic in place, so that user data is protected and initialized correctly. | Must | 8 | 1 | Done |  | 1. Core profile, onboarding, check-in, action, and summary tables or collections exist for V1. 2. Row-level security prevents cross-user data access under authenticated conditions. 3. A new authenticated user receives a linked profile record automatically. 4. Timezone, onboarding completion state, and display name can be persisted safely. 5. Migration or schema setup can be run repeatably in a fresh environment. 6. Security checks cover private content such as journal entries.
PBI-005 | Technical Foundation | As the system, I want normalized action events and weekly summary generation handled on the backend, so that official scores remain authoritative and auditable. | Must | 8 | 5 | Done |  | 1. Score-relevant writes produce normalized backend-owned action events. 2. Weekly domain summaries and weekly life summaries are generated from backend logic, not client writes. 3. Official summaries include balanced life score, life strength, evenness, strongest domain, and weakest domain. 4. Historical official summaries are persisted for later reads. 5. Backend processing prevents duplicate scoring from edits or repeated writes. 6. Operational logs or audit fields make summary generation traceable for debugging.
PBI-006 | Authentication & Session | As a new or returning user, I want to sign up and sign in with email and password, so that I can securely access my account and saved data. | Must | 5 | 1 | Done |  | 1. User can create an account with email and password. 2. User can sign in with valid email and password credentials. 3. Invalid credentials return a clear user-friendly error message. 4. Successful authentication routes the user into the correct next flow. 5. Auth screens are usable on common phone sizes in portrait orientation.
PBI-007 | Authentication & Session | As a returning user, I want my session restored and protected routes enforced, so that I can reopen the app without friction while keeping account access secure. | Must | 3 | 2 | Done |  | 1. App restores a valid existing session on reopen. 2. Unauthenticated users are routed to auth screens before score-related content is shown. 3. Authenticated users cannot see auth screens unless they sign out. 4. Sign-out clears local session state and returns the user to auth. 5. Protected routing works correctly across app reloads and cold starts.
PBI-008 | Onboarding | As a first-time user, I want welcome framing plus display name and timezone setup, so that I understand the product and establish the correct scoring context. | Must | 3 | 2 | Done |  | 1. Onboarding begins with short product framing that explains the five-domain model. 2. User can enter a display name before score features become active. 3. User can choose or confirm a scoring timezone. 4. Timezone input is validated before onboarding submission continues. 5. Onboarding progress is visually clear and mobile-friendly.
PBI-009 | Onboarding | As a first-time user, I want to complete a five-domain baseline quiz, so that the app can create my starting balance profile. | Must | 5 | 2 | Done |  | 1. Quiz collects one rating from 1 to 5 for each of the five domains. 2. User can review and change answers before final submission. 3. Progress through the quiz is visible. 4. Submitted ratings are mapped to the expected score scale for onboarding baselines. 5. Successful completion routes the user into the main app shell.
PBI-010 | Onboarding | As the system, I want onboarding submission to persist one baseline per domain and mark onboarding complete once, so that bootstrap scoring stays correct. | Must | 5 | 2 | Done |  | 1. Submitting onboarding creates one baseline record for each domain. 2. Profile is marked as onboarding complete after a valid submission. 3. Duplicate normal onboarding submissions are prevented. 4. Bootstrap-period fields needed by score logic are stored correctly. 5. If submission fails, the user sees a recoverable error state rather than silent data loss.
PBI-011 | Dashboard & Summary | As a user, I want the home dashboard to show my latest official Balanced Life Score and quick actions, so that I can understand my current state immediately. | Must | 5 | 2 | Done |  | 1. Home dashboard displays the latest official Balanced Life Score when one exists. 2. Quick actions for daily check-in and action logging are visible without deep navigation. 3. Dashboard can open from cached state before a full refresh completes. 4. If no official summary exists yet, the screen shows a meaningful empty state. 5. Loading and refresh behavior is visible and understandable.
PBI-012 | Dashboard & Summary | As a user, I want to see strongest and weakest domains plus my five domain scores on home, so that I know where to focus next. | Must | 3 | 3 | Done |  | 1. Dashboard shows five domain scores in a consistent product-defined order. 2. Strongest and weakest domains are highlighted using the latest official summary. 3. Domain labels remain readable on small phone widths. 4. Quick glance information does not require scrolling past the first viewport on common devices. 5. Domain data matches the persisted backend summary payload.
PBI-013 | Dashboard & Summary | As a user, I want a radar or wheel visualization of my five domains, so that I can interpret balance at a glance. | Should | 3 | 3 | Done |  | 1. Visualization displays all five VELORA domains on a shared 0 to 100 scale. 2. Chart renders legibly on common iOS and Android phone sizes. 3. Visualization reflects the same official summary values shown in the score list. 4. Chart styling matches the calm, structured UI direction. 5. If chart data is unavailable, dashboard falls back to a readable non-chart state.
PBI-014 | Daily Check-In | As a user, I want to complete a five-domain daily check-in in under a minute, so that reflection is easy to maintain. | Must | 5 | 3 | Done |  | 1. Check-in presents one rating control for each of the five domains. 2. Controls are touch-friendly and provide immediate visual confirmation. 3. User can submit the full daily check-in from one screen. 4. The flow is short enough to complete quickly on a phone. 5. Submission success clearly confirms that today's reflection has been saved.
PBI-015 | Daily Check-In | As a user, I want to edit today's check-in and see save or pending-sync feedback, so that I trust my reflection data is correct. | Must | 5 | 3 | Done |  | 1. System allows at most one check-in per domain per local scoring day. 2. If a check-in already exists for today, the user sees edit state instead of duplicate-entry state. 3. Updated ratings upsert the same record rather than creating duplicates. 4. Timezone-aware local scoring date is derived consistently. 5. Pending sync, success, and failure states are clearly communicated to the user.
PBI-016 | Actions Hub | As a user, I want a domain-grouped actions hub, so that I can quickly navigate to the right logging tool. | Must | 3 | 3 | Done |  | 1. Actions tab groups tools by their associated domain. 2. Each tile or row is clearly labeled by purpose, not internal system language. 3. Tapping a tool opens the correct logging screen. 4. Hub layout remains simple and predictable on small screens. 5. Navigation back to home or other tabs remains consistent with the app shell.
PBI-017 | Spirituality | As a user, I want to create, edit, and browse journal entries, so that I can reflect intentionally and build spirituality evidence over time. | Must | 5 | 3 | Done |  | 1. User can create a journal entry with non-empty body text. 2. User can edit an existing journal entry safely. 3. User can browse prior journal entries in a list view. 4. Creating or editing an entry results in the correct normalized journal action handling on the backend. 5. Journal content is only visible to the owning authenticated user.
PBI-018 | Family & Friends | As a user, I want to log meaningful connections with optional context, so that I can maintain relationships and see that effort reflected in the app. | Must | 3 | 4 | Done |  | 1. User can create a meaningful connection log with at least one meaningful signal such as type, contact label, or note. 2. User can edit an existing connection log. 3. Connection logs are listed in reverse chronological order. 4. Normalized backend action handling respects the daily cap and avoids duplicate scoring on edits. 5. Screen copy makes it clear that simple, real-world connection effort is being tracked.
PBI-019 | Work/Productivity | As a user, I want to create and complete important tasks, so that I can track meaningful progress in the work and productivity domain. | Must | 5 | 4 | Done |  | 1. User can create a task with title and optional notes. 2. User can update task text before completion. 3. Completing a task generates a score-relevant event only on the first transition to completed. 4. Editing a completed task does not create duplicate score events. 5. Completed tasks cannot be reverted in a way that breaks score integrity rules.
PBI-020 | Work/Productivity | As a user, I want to log focused work sessions, so that deep work contributes alongside completed tasks. | Should | 3 | 4 | Done |  | 1. User can start, complete, and cancel a focus session. 2. Completed sessions record duration from start and end times. 3. Only completed sessions create normalized focus-session events. 4. Completed session timing cannot be arbitrarily rewritten afterward. 5. Focus session history is visible in a basic list or recent-history view.
PBI-021 | Health | As a user, I want to log activities with type and optional duration or note, so that I can track movement and support the health domain. | Must | 3 | 4 | Done |  | 1. User can create an activity log with non-empty activity type. 2. Optional fields such as duration, distance, or note are supported without blocking simple entry. 3. User can edit an existing activity log. 4. Activity logs appear in recent history or list form. 5. Normalized exercise action handling updates correctly when an activity log is edited.
PBI-022 | Health | As a user, I want to log sleep sessions and review recent sleep records, so that I can see how recovery contributes to wellbeing. | Should | 3 | 4 | Done |  | 1. User can log sleep start and sleep end times. 2. System derives sleep duration and assigns the record to the wake-up day. 3. User can correct a sleep log later without creating duplicate score events. 4. Recent sleep records are viewable in a simple list. 5. Sleep log handling respects the documented scoring date rules.
PBI-023 | Financial Wellbeing | As a user, I want to log expenses with category, amount, currency, and date, so that I can build awareness of my financial habits. | Must | 5 | 4 | Done |  | 1. User can create an expense with positive amount, category, and currency. 2. Currency validation enforces a 3-letter uppercase currency code. 3. User can edit an existing expense log. 4. Expense logs are listed in recent history. 5. Normalized expense action handling updates safely on edits and respects daily caps.
PBI-024 | Financial Wellbeing | As a user, I want to log budget reviews or savings actions, so that deliberate finance behaviors count even when I do not record a purchase. | Should | 3 | 5 | Done |  | 1. User can create a financial action with a non-empty action kind. 2. Optional amount is stored only when positive. 3. User can edit an existing financial action. 4. Financial actions appear in recent history or the relevant module list. 5. Normalized budget-review or savings-action handling updates safely on edits.
PBI-025 | Dashboard & Summary | As a user, I want a weekly summary detail screen showing Balanced Life Score, life strength, evenness, and domain breakdown, so that weekly review feels meaningful. | Must | 5 | 5 | Done |  | 1. Weekly summary detail reads from persisted official summary data. 2. Screen shows balanced life score, life strength, evenness, strongest domain, and weakest domain. 3. Five domain breakdown values are shown clearly and consistently. 4. If the viewed week is incomplete or provisional, the UI labels that state explicitly. 5. Screen links the user back to home and onward to action-taking paths.
PBI-026 | Dashboard & Summary | As a user, I want a summary history list and simple domain trend views, so that I can compare my weekly progress over time. | Should | 5 | 5 | Done |  | 1. User can browse prior weekly summaries in reverse chronological order. 2. History reads persisted official summaries rather than recomputing on the client. 3. User can inspect recent score movement for the overall score or per-domain data. 4. Missing historical data is handled gracefully with a clear empty state. 5. History loading remains performant on mobile devices.
PBI-027 | Missions & Streaks | As a user, I want lightweight weekly missions based on weaker domains, so that I have clear next steps after reviewing my summary. | Should | 5 | 5 | Done |  | 1. User can view currently assigned weekly missions. 2. Missions are clearly associated with relevant domains or improvement themes. 3. User can mark a mission complete. 4. Mission completion state is reflected in the UI and stored for the current week. 5. Mission UX supports guidance without presenting missions as the source of score truth.
PBI-028 | Missions & Streaks | As a user, I want my current streak shown on the dashboard, so that consistent use feels visible without becoming the main score. | Should | 3 | 6 | Done |  | 1. Dashboard displays the current streak count in a lightweight way. 2. Streak updates are based on qualifying behavior defined by the backend or shared rules. 3. Missed qualifying days break the streak according to the agreed rule set. 4. Streak status does not replace or distort the official balance score presentation. 5. If streak data is unavailable, the dashboard fails gracefully.
PBI-029 | Settings & Experience | As a user, I want a settings screen with profile, timezone display, and account actions, so that I can manage my account safely. | Must | 3 | 6 | Done |  | 1. Settings shows display name and basic account context. 2. Settings shows the current scoring timezone clearly. 3. User can access sign-out from settings. 4. Safe non-scoring profile edits are supported where allowed. 5. Settings screen follows the same visual system as the rest of the app.
PBI-030 | Settings & Experience | As a user, I want clear loading, empty, error, and offline states across core screens, so that the app feels understandable even when data is missing or syncing. | Must | 5 | 6 | Done |  | 1. Home, check-in, actions, and summary flows have explicit loading states. 2. Core screens provide helpful empty states that explain what to do next. 3. Offline or pending-sync states are visible where writes can queue locally. 4. User-facing errors are short, actionable, and never expose raw backend details. 5. Primary actions remain visible and readable on small phone screens. 6. Color is not the only indicator used for important status or score state.
PBI-031 | Quality & Release | As a team, we want automated validation of scoring logic, protected data flows, and critical mobile journeys, so that V1 is shippable and trustworthy. | Must | 5 | 6 | Done |  | 1. Automated tests cover core score calculations and onboarding bootstrap behavior. 2. Automated tests cover at least one happy-path auth journey and one daily check-in journey. 3. Validation covers protected data access boundaries for at least core user-owned data. 4. Release checklist includes environment setup, migration readiness, and rollback considerations. 5. Known release blockers are documented before V1 sign-off.

## Sprint Plan
Sprint | Weeks | Focus | PBI IDs | Total Story Points | Goal
1 | Weeks 1-2 | Foundation + Auth | PBI-001, PBI-002, PBI-003, PBI-004, PBI-006 | 26 | A runnable mobile shell, secure backend foundation, and first working authentication flow are in place.
2 | Weeks 3-4 | Onboarding + Home Entry | PBI-007, PBI-008, PBI-009, PBI-010, PBI-011 | 21 | Users can sign in, complete onboarding, and land on a working home dashboard entry point.
3 | Weeks 5-6 | Check-In + Core Daily Loop | PBI-012, PBI-013, PBI-014, PBI-015, PBI-016, PBI-017 | 24 | The daily loop is real: users can review home context, check in, open the actions hub, and journal.
4 | Weeks 7-8 | Domain Logging v1 | PBI-018, PBI-019, PBI-020, PBI-021, PBI-022, PBI-023 | 22 | All core everyday logging paths for relationships, productivity, health, and finance are usable end to end.
5 | Weeks 9-10 | Weekly Review + Guidance | PBI-005, PBI-024, PBI-025, PBI-026, PBI-027 | 26 | Official weekly summaries, history, and mission guidance make the weekly review loop meaningful.
6 | Weeks 11-12 | Settings + Hardening + Release | PBI-028, PBI-029, PBI-030, PBI-031 | 16 | The app is resilient, understandable, and release-ready with clear settings, UX states, and validation coverage.

## Epic Summary
Epic | Total PBIs | Must | Should | Could | Total Story Points | Sprints Involved
Technical Foundation | 5 | 5 | 0 | 0 | 29 | 1, 5
Authentication & Session | 2 | 2 | 0 | 0 | 8 | 1, 2
Onboarding | 3 | 3 | 0 | 0 | 13 | 2
Dashboard & Summary | 5 | 3 | 2 | 0 | 21 | 2, 3, 5
Daily Check-In | 2 | 2 | 0 | 0 | 10 | 3
Actions Hub | 1 | 1 | 0 | 0 | 3 | 3
Spirituality | 1 | 1 | 0 | 0 | 5 | 3
Family & Friends | 1 | 1 | 0 | 0 | 3 | 4
Work/Productivity | 2 | 1 | 1 | 0 | 8 | 4
Health | 2 | 1 | 1 | 0 | 6 | 4
Financial Wellbeing | 2 | 1 | 1 | 0 | 8 | 4, 5
Missions & Streaks | 2 | 0 | 2 | 0 | 8 | 5, 6
Settings & Experience | 2 | 2 | 0 | 0 | 8 | 6
Quality & Release | 1 | 1 | 0 | 0 | 5 | 6
TOTAL | 31 | 24 | 7 | 0 | 135

## Legend & Guide
BACKLOG GUIDE
PRIORITY (MoSCoW)
Must | App cannot launch without this. Core to the product hypothesis.
Should | Important for a good product. Implement after Must items.
Could | Nice-to-have. Only if time permits.
STATUS
To Do | Not yet started.
In Progress | Currently being worked on.
In Review | Code complete, awaiting review/testing.
Done | Meets all acceptance criteria and tested.
STORY POINTS
1 | Trivial — a few hours of work.
2 | Small — less than a day.
3 | Medium — 1-2 days.
5 | Large — 2-3 days.
8 | Very large — nearly a full week. Consider splitting.
13 | Too big — must be broken into smaller stories.
ACCEPTANCE CRITERIA
Definition | A checklist of conditions that must ALL be true for a PBI to be marked 'Done'.
Purpose | Removes ambiguity. Team and stakeholder agree on what 'done' means.
Format | Numbered list of testable statements.